## Slide 1
Project Description
The goal of the research is to study magnetohydrodynamic turbulence by maintaining a constant magnetic Prandtl number (PrM) and varying its defining parameters - Reynolds number (Re) and magnetic Reynolds number (ReM). Doing this over a range of PrM it is possible to compare the results to previous findings ([1] for example). If time allows it, a study on the use of high-k forcing to inject helicity to a similar system and compare with the varying PrM results will be also performed.
Numerical Study of Homogeneous Turbulence for Varying Magnetic Prandtl Number
Andrés Cathey
Supervisors: Prof. Arjun Berera and Ms Mairi McKay
This poster outlines a plan and a rough schedule for the preparation and fullfilment of my MSc dissertation project. It is, of course, subject to change.
Task | Start | End
Theory review | June 1 | June 10
Existing code review and learning MPI | June 10 | June 24
Data acquisition | June 24 | July 15
Data analysis and comparison to literature | July 15 | July 31
Write report | August 1 | August 14
Presentation preparation | August 14 | August 16
*Weekly/Biweekly meetings |  | 
Methodology
In order to perform the numerical calculations, the use of High Performance Computing hardware (ARCHER or eddie), will be required since the code that will be used relies heavily on parallelisation - Message Passing Interface (MPI) must be learnt to do so. To obtain the desired data a pseudospectral code which simulates a cubic box of N3 grid points with periodic boundary conditions will be used. The output data can be analysed and compared with existing literature.
Report Structure
The report for the MSc dissertation project will include an introduction to the field of magnetohydrodynamics and to the methods required for the numerical calculations that were preformed. Benchmarking procedures to ensure the numerical calculations accurately reproduce previous results will also be included. Finally, an analysis of the performed computations will be included and commented on.
[1] Brandenburg, A. (2014). Magnetic Prandtl number dependence of the kinetic-to-magnetic dissipation ratio. The Astrophysical Journal, 791(1), 12. Chicago